**Marketing Plan for spring 2016 We’re Ready! Workshops**

**Project Phase 2 Goal:** Implementing the Neighbourhood Disaster Program Pilot Project.

**Marketing Plan Objectives:**

* To gain community awareness of the ‘We’re Ready! Project.
* To enlist participants for the May 28 and May 29 workshops (40 per workshop)

**Marketing Plan:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **Timeframe** | **Responsibility** | **Budget** |
| Radio Interviews (Sun Country and AM1140) | Week of May 16, public service announcements from May 16th until event  | Gayelle and Judy  | $0 |
| Flyers (door to door delivery) * needs to be designed and printed
 | Week of April 15th  | Whole committee for delivery or hire a delivery person  | $300 (design and printing)$200 (delivery) |
| Newspaper story  | Week of April 15 and week of May 16 | Gayelle and Judy  | $0 |
| Our High River website  | Week of April 15 and week of May 16 | Judy  | $0 |
| FCSS E-Mail Fan Out  | April and May  | Judy  | $0 |
| Posters about Town  | April 1  | Whole committee for delivery and hanging  | $200 (design and printing)$100 (delivery)  |
| Foothills Immigrants Services Fan Out  | April and May  | Lisa and Mary-Joy | $100 (flyers or email) |
| Filipino Association  | April and May  | Lisa and Mary-Joy | $100 (flyers or email) |
| Ministerial Association  | April and May  | Gayelle and Judy  | $25 (flyers) |
| Community Organizations (Library, hospital, Narrow Road Home, schools, Chamber of Commerce, Manor, etc.)  | April and May  | Whole committee for delivery of flyers and posters/or hire a delivery person  | $100 (delivery) |
| **Total Budget**  | **$1,125.00\*** |

\*Budget has 2 categories: 1. design and printing and 2. delivery of flyers and posters